## Issues Table
Issue Number | Name | Description | Assigned To | Creator | Created By | Priority | Status | Type | Account | Created On | Due Date | Last Updated | Deadline
1 | Haven't requested | please revert back | Architect | Architect | Bogdan_D | high | for approval | Diff | Demo_3D_Repo | 2021-01-28 | 2021-01-29 | 2021-03-24 18:53 | Overdue
2 | Extra Seating | Can we provide some additional public benches here? | Landscape Designer | Architect | Bogdan_D | low | in progress | Design | Demo_3D_Repo | 2020-03-25 | 2020-04-03 | 2021-03-24 18:53 | Overdue
3 | Clash 01 | Please investigate | Structural Engineer | 3D Repo | jackwilliams | low | open | Clash | Demo_3D_Repo | 2021-03-15 |  | 2021-03-24 18:53 | On Time
4 | Central Building roof landscape design | Can you please add the roof layout to your next model revision, so we could check the slab's structural integrity. | Structural Engineer | Structural Engineer | Maria_Arjona | low | in progress | For information | Demo_3D_Repo | 2020-03-25 | 2020-03-30 | 2021-03-24 18:53 | Overdue
5 | Extra Trees | Could we have some trees in this green space? | Landscape Designer | Architect | Bogdan_D | high | open | Design | Demo_3D_Repo | 2020-03-25 | 2020-04-03 | 2021-03-24 18:53 | Overdue
6 | Clash | MEP is not going through the opening | MEP Engineer | 3D Repo | jackwilliams | high | closed | Clash | Demo_3D_Repo | 2020-10-02 | 2020-10-31 | 2021-03-24 18:53 | On Time
7 | Garden Gates | Are you providing any access restricting gates here? | Landscape Designer | Architect | Bogdan_D | low | open | Design | Demo_3D_Repo | 2020-03-25 | 2021-03-31 | 2021-03-24 18:53 | Overdue
8 | Soil waste pipe position (Terraced Houses) | Review this clash with the coping stone | Structural Engineer | Architect | Bogdan_D | high | in progress | Design | Demo_3D_Repo | 2020-03-25 | 2020-03-31 | 2021-03-24 18:53 | Overdue
9 | Cable tray Junction - Roof Level, North Wing | What do we do here? Do we need to update our slab opening or you are still working on this? | Structural Engineer | Structural Engineer | Maria_Arjona | medium | for approval | Clash | Demo_3D_Repo | 2020-03-25 | 2020-04-03 | 2021-03-24 18:53 | Overdue
10 | Retaining wall openings for the Pipes | Basement Level | Structural Engineer | MEP Engineer | Kurt_Smith | medium | closed | Design | Demo_3D_Repo | 2020-03-25 | 2020-04-03 | 2021-03-24 18:53 | On Time
11 | Window opening in the wall required | Review the window layout | Structural Engineer | Architect | Bogdan_D | medium | closed | Design | Demo_3D_Repo | 2020-03-25 | 2020-03-27 | 2021-03-24 18:53 | On Time
12 | Roof Level Slab opening | We need a sufficient slab opening here for the Duct pipe | MEP Engineer | MEP Engineer | Kurt_Smith | low | for approval | Clash | Demo_3D_Repo | 2020-03-25 | 2020-03-26 | 2021-03-24 18:53 | Overdue
13 | Pipe clashing | update the opening | Architect | Architect | Bogdan_D | medium | closed | Clash | Demo_3D_Repo | 2020-03-25 | 2020-03-31 | 2021-03-24 18:53 | On Time
14 | No Slab openings for the waste pipe | Provide slab openings at each level | MEP Engineer | MEP Engineer | Kurt_Smith | high | for approval | Clash | Demo_3D_Repo | 2020-03-25 | 2020-04-03 | 2021-03-24 18:53 | Overdue
15 | No slab opening | Provide slab opening for the rainwater pipe ID:322909 | MEP Engineer | MEP Engineer | Kurt_Smith | low | in progress | Clash | Demo_3D_Repo | 2020-03-25 | 2020-04-03 | 2021-03-24 18:53 | Overdue
16 | Adjust the layout of slab openings | Move the slab openings to suit Pipe positions | Structural Engineer | MEP Engineer | Kurt_Smith | none | open | Clash | Demo_3D_Repo | 2020-03-25 | 2020-04-03 | 2021-03-24 18:53 | Overdue
17 | Untitled Issue | (No Description) | MEP Engineer | 3D Repo | Joe_Lawson | none | open | AR | Demo_3D_Repo | 2021-03-17 | 2021-03-18 | 2021-03-24 18:53 | Overdue
18 | Slab Opening missing | Provide an additional opening for the cable tray | MEP Engineer | MEP Engineer | Kurt_Smith | medium | for approval | Clash | Demo_3D_Repo | 2020-09-14 | 2020-09-25 | 2021-03-24 18:53 | Overdue
19 | Asset 01 | Vaillant Boiler unit | Architect | Architect | Bogdan_D | high | for approval | FM | Demo_3D_Repo | 2020-04-27 | 2020-04-24 | 2021-03-24 18:53 | Overdue
20 | Pipe Clash | Move them | Architect | Architect | Bogdan_D | low | in progress | Clash | Demo_3D_Repo | 2020-03-26 | 2020-03-31 | 2021-03-24 18:53 | Overdue
21 | CLash here | (No Description) | MEP Engineer | Architect | Bogdan_D | high | closed | Clash | Demo_3D_Repo | 2020-06-05 | 2020-05-22 | 2021-03-24 18:53 | On Time
22 | Move pipe into opening | (No Description) | MEP Engineer | 3D Repo | jackwilliams | high | closed | Clash | Demo_3D_Repo | 2020-08-14 | 2020-08-31 | 2021-03-24 18:53 | On Time
23 | Roof Access Hatch | Provide an access | Architect | Architect | Bogdan_D | medium | in progress | Design | Demo_3D_Repo | 2020-03-30 | 2020-03-31 | 2021-03-24 18:53 | Overdue
24 | Ceiling Height | Not sufficient, needs to be 3m | Architect | Architect | Bogdan_D | high | closed | Design | Demo_3D_Repo | 2020-09-09 | 2020-09-11 | 2021-03-24 18:53 | On Time
25 | Clash | (No Description) | 3D Repo | 3D Repo | jackwilliams | high | closed | Clash | Demo_3D_Repo | 2020-09-11 | 2020-09-30 | 2021-03-24 18:53 | On Time
26 | We didn't request this | Please have a look | MEP Engineer | Architect | Bogdan_D | high | closed | Diff | Demo_3D_Repo | 2020-09-10 | 2020-09-11 | 2021-03-24 18:53 | On Time
27 | I did not spec this | (No Description) | Architect | Architect | Bogdan_D | none | closed | Diff | Demo_3D_Repo | 2020-05-20 | 2020-05-22 | 2021-03-24 18:53 | On Time
28 | What is going on with this opening? | Do we need to adjust it? Is the pipe location fixed? | MEP Engineer | 3D Repo | Demo_3D_Repo | medium | closed | For information | Demo_3D_Repo | 2020-04-27 | 2020-04-29 | 2021-03-24 18:53 | On Time
29 | Clash 01 | Please move pipe in to the opening | 3D Repo | 3D Repo | jackwilliams | high | for approval | Clash | Demo_3D_Repo | 2020-08-20 | 2021-02-26 | 2021-03-24 18:53 | Overdue
30 | Cable tray not supposed to be here | (No Description) | Architect | Architect | Bogdan_D | high | closed | Clash | Demo_3D_Repo | 2020-08-25 | 2020-08-31 | 2021-03-24 18:53 | On Time
31 | Windows Layout | Update window locations | Project Manager | Architect | Bogdan_D | low | closed | For information | Demo_3D_Repo | 2020-04-15 | 2020-04-24 | 2021-03-24 18:53 | On Time
32 | Layout here | Review the MEP Layout | Architect | Architect | Bogdan_D | high | closed | For information | Demo_3D_Repo | 2020-04-01 | 2020-03-31 | 2021-03-24 18:53 | On Time
33 | Apartment layout | can we rearrange the furniture here? | Architect | Architect | Bogdan_D | none | for approval | Design | Demo_3D_Repo | 2020-03-30 | 2021-04-15 | 2021-03-24 18:53 | Overdue
34 | update facade model please | Wall junction is missing | Project Manager | Project Manager | anorrie | low | for approval | Design | Demo_3D_Repo | 2020-03-26 | 2020-03-31 | 2021-03-24 18:53 | Overdue
35 | Slab | Missing slab in the model | Architect | Architect | Bogdan_D | low | for approval | For information | Demo_3D_Repo | 2020-04-01 | 2020-03-31 | 2021-03-24 18:53 | Overdue
36 | Kitchen units are blocking the window | review | Architect | Architect | Bogdan_D | high | for approval | Design | Demo_3D_Repo | 2020-03-30 | 2020-03-31 | 2021-03-24 18:53 | Overdue
37 | MEP Unit Clashing with the structural ramp | Update the placement | Architect | Architect | Bogdan_D | high | in progress | Constructibility | Demo_3D_Repo | 2020-03-25 | 2020-03-27 | 2021-03-24 18:53 | Overdue
38 | Bedroom opening drylining | Update the detail | Architect | Architect | Bogdan_D | none | open | Constructibility | Demo_3D_Repo | 2020-03-30 | 2020-03-31 | 2021-03-24 18:53 | Overdue
39 | pipes | (No Description) | MEP Engineer | Architect | Bogdan_D | high | open | Clash | Demo_3D_Repo | 2021-02-05 |  | 2021-03-24 18:53 | On Time
40 | Bench Height | (No Description) | Architect | Architect | Bogdan_D | medium | closed | Design | Demo_3D_Repo | 2020-11-18 | 2020-11-20 | 2021-03-24 18:53 | On Time
41 | Opening | Not big enough | Structural Engineer | Architect | Bogdan_D | medium | closed | For information | Demo_3D_Repo | 2020-11-11 |  | 2021-03-24 18:53 | On Time
42 | No Slab opening here | Provide an additional opening here | MEP Engineer | MEP Engineer | Kurt_Smith | medium | for approval | Clash | Demo_3D_Repo | 2020-09-22 | 2020-09-25 | 2021-03-24 18:53 | Overdue
43 | What's happening here? | fix this | Architect | Architect | Bogdan_D | high | closed | Diff | Demo_3D_Repo | 2020-09-22 | 2020-09-25 | 2021-03-24 18:53 | On Time
44 | Clash | Please move pipe into slab opening | 3D Repo | 3D Repo | jackwilliams | high | for approval | Clash | Demo_3D_Repo | 2020-10-02 | 2021-02-05 | 2021-03-24 18:53 | Overdue
45 | Windows non compliant | (No Description) | Architect | Architect | Bogdan_D | high | in progress | Design | Demo_3D_Repo | 2021-02-05 |  | 2021-03-24 18:53 | On Time
46 | Demo Project | kyhgcykhcgtykhc |  | 3D Repo | Joe_Lawson | none | open | Clash | Demo_3D_Repo | 2021-02-17 | 2021-02-22 | 2021-03-24 18:53 | Overdue
47 | Ceiling height | (No Description) | MEP Engineer | Architect | Bogdan_D | high | open | Design | Demo_3D_Repo | 2020-12-07 | 2020-12-25 | 2021-03-24 18:53 | Overdue
48 | Pipe location | Move pipe to slab opening location |  | 3D Repo | Demo_3D_Repo | high | for approval | Clash | Demo_3D_Repo | 2020-12-12 | 2020-12-19 | 2021-03-24 18:53 | Overdue
49 | Claim | Why has this changed from the previous revision? | 3D Repo | 3D Repo | jackwilliams | medium | for approval | Diff | Demo_3D_Repo | 2020-12-09 | 2020-12-23 | 2021-03-24 18:53 | Overdue
50 | new clash | rtwh | MEP Engineer | 3D Repo | Joe_Lawson | medium | for approval | Constructibility | Demo_3D_Repo | 2021-02-03 | 2021-02-10 | 2021-03-24 18:53 | Overdue
51 | Fire Report | Have a look and review | Architect | Architect | Bogdan_D | medium | closed | Design | Demo_3D_Repo | 2020-12-01 | 2020-12-04 | 2021-03-24 18:53 | On Time
52 | PowerBI DashBoard | https://app.powerbi.com/view?r=eyJrIjoiYjc4ZmI1MzgtMzQzOS00NDk5LWI4N2QtODE2ZWVlZWFlNmZkIiwidCI6IjUwMTc3OWVlLTc3ZDQtNDJjZi04ZWRhLWZiNWU0YTAzYWI3MSJ9 | Project Manager | Project Manager | anorrie | none | for approval | RFI | Demo_3D_Repo | 2021-01-12 |  | 2021-03-24 18:53 | On Time
53 | Hard Clash 01 | Pentetration through slab | Structural Engineer | 3D Repo | jackwilliams | low | open | Clash | Demo_3D_Repo | 2021-01-13 | 2021-01-31 | 2021-03-24 18:53 | Overdue
54 | Clash 01 | MEP going through slap | MEP Engineer | 3D Repo | jackwilliams | low | open | Clash | Demo_3D_Repo | 2021-02-05 | 2021-02-25 | 2021-03-24 18:53 | Overdue
55 | Clash 01 | MEP not going through slab opening | 3D Repo | 3D Repo | jackwilliams | low | open | Clash | Demo_3D_Repo | 2021-01-14 | 2021-01-31 | 2021-03-24 18:53 | Overdue
56 | test | (No Description) | 3D Repo | 3D Repo | Joe_Lawson | high | for approval | Clash | Demo_3D_Repo | 2021-02-24 | 2021-02-26 | 2021-03-24 18:53 | Overdue
57 | new issue | (No Description) |  | 3D Repo | Joe_Lawson | high | for approval | AR | Demo_3D_Repo | 2021-03-08 |  | 2021-03-24 18:53 | On Time
58 | Clash 01 | Please can you investigate this | Structural Engineer | 3D Repo | jackwilliams | low | open | Clash | Demo_3D_Repo | 2021-03-09 | 2021-03-31 | 2021-03-24 18:53 | Overdue
59 | Clash 01 | Please move in to slab opening | Structural Engineer | 3D Repo | jackwilliams | low | in progress | Clash | Demo_3D_Repo | 2021-03-11 | 2021-03-30 | 2021-03-24 18:53 | Overdue
60 | Size change | Chnage in geometry in MEP | 3D Repo | 3D Repo | jackwilliams | medium | for approval | Diff | Demo_3D_Repo | 2021-03-16 | 2021-03-31 | 2021-03-24 18:53 | Overdue
61 | waterproofing? | (No Description) | 3D Repo | 3D Repo | Joe_Lawson | high | open | Constructibility | Demo_3D_Repo | 2021-03-17 | 2021-03-18 | 2021-03-24 18:53 | Overdue
62 | new issue | (No Description) |  | 3D Repo | Joe_Lawson | high | for approval | AR | Demo_3D_Repo | 2021-03-17 |  | 2021-03-24 18:53 | On Time